## Sheet1
Task Layout
| Task Name | Start | Duration | Finish | Allocated Members | Type
Phase 1 - Planning | Project Initiation | 2020-03-16 | 1d | 2020-03-16 | All | Milestone
| Draft Game Mechanics | 2020-03-16 | 1d | 2020-03-17 | All | Task
| Implement initial concept design documentation | 2020-03-16 | 1d | 2020-03-17 | All | Task
| Game Mechanics - Draft Hunter & Ghost Capabilities | 2020-03-17 | 6d | 2020-03-23 | All | Task
| Game Mechanics - Draft Winning / Losing Conditions | 2020-03-17 | 6d | 2020-03-23 | All | Task
| Game Mechanics - Draft Level Design & Relevant assets | 2020-03-17 | 6d | 2020-03-23 | Eleanor | Task
| Game Mechanics - Draft Networking States | 2020-03-17 | 6d | 2020-03-23 | All | Task
| Game Mechanics - Draft UI, including AirConsole Controller | 2020-03-17 | 6d | 2020-03-23 | All | Task
| Game Mechanics - Draft UI Navigation and States | 2020-03-17 | 6d | 2020-03-23 | All | Task
| Aesthetics - Draft Aesthetics, Models, Textures and Animations | 2020-03-17 | 6d | 2020-03-23 | Efran | Task
| Aesthetics - Draft Light Placement and Sound | 2020-03-17 | 6d | 2020-03-23 | All | Task
| Implement Air Console within the project | 2020-03-23 | 7d | 2020-03-31 | Damon, Olumide, Stephan | Task
| Implement Hunter / Ghost Movement | 2020-03-23 | 7d | 2020-03-31 | Olumide | Task
| Implement Light Sources | 2020-03-23 | 7d | 2020-03-31 | Damon | Task
| Finalize Task List & New Time Plan | 2020-03-23 | 8d | 2020-04-01 | Damon | Task
| Finalize Concept Design Documentation | 2020-03-23 | 8d | 2020-04-01 | Eleanor, Efran, Stephan | Task
| Finalize Market Research Documentation | 2020-03-23 | 8d | 2020-04-01 | Olumide | Task
| Finalize UML Diagrams of proposed features | 2020-03-23 | 8d | 2020-04-01 | Stephan | Task
| Finalize Art and Sound Concepts and implement into document | 2020-03-23 | 8d | 2020-04-01 | Efran | Task
| Phase 1 Completion | 2020-04-01 | 1d | 2020-04-01 | All | Milestone
Phase 2 - Implementation | Implement UI Transitions and functionality | 2020-04-02 | 7d | 2020-04-09 | Stephan | Task
| Implement Level Design within the Game World | 2020-04-02 | 7d | 2020-04-09 | Eleanor, Efran | Task
| Implement Character Interaction Mechanics - Hunter | 2020-04-02 | 7d | 2020-04-09 | Olumide, Damon | Task
| Implement Character Interaction Mechanics - Ghost | 2020-04-02 | 7d | 2020-04-09 | Olumide, Damon | Task
| Implement Small & Large Object Mechanics | 2020-04-02 | 7d | 2020-04-09 | Eleanor, Efran | Task
| Implement Winning / Losing Conditions | 2020-04-02 | 7d | 2020-04-09 | Stepan | Task
| Implement Spawning and Hosting of the game | 2020-04-09 | 6d | 2020-04-15 | Olumide, Damon | Task
| Implement Atmospheric Effects | 2020-04-09 | 6d | 2020-04-15 | Efran | Task
| Implement Art Files | 2020-04-09 | 6d | 2020-04-15 | Efran | Task
| Implement Sound Files | 2020-04-09 | 6d | 2020-04-15 | Efran, Eleanor | Task
| Buffer Period for Major Bug Fixing or inclusion of needed changes | 2020-04-09 | 6d | 2020-04-15 | All | Task
| Finalize Remaining Minor Features / Bug Fixing | 2020-04-09 | 6d | 2020-04-15 | All | Task
| Phase 2 Completion | 2020-04-15 | 1d | 2020-04-15 | All | Milestone
Phase 3 - Testing | Bug Fix and Refactor Gameplay Elements | 2020-04-15 | 5d | 2020-04-20 | Olumide, Damon | Task
| Complete Design Documentation and Help Guide | 2020-04-15 | 5d | 2020-04-20 | All | Task
| Bug Fix and Refactor UI Elements | 2020-04-15 | 5d | 2020-04-20 | Stephan | Task
| Bug Fix and Refactor AirConsole and Multiplayer Elements | 2020-04-20 | 5d | 2020-04-24 | Olumide, Damon | Task
| Bug Fix and make necessary changes to Art & Sound | 2020-04-20 | 5d | 2020-04-24 | Efran, Eleanor | Task
| Finalize All Changes and Player Test | 2020-04-20 | 5d | 2020-04-24 | All | Task
| Phase 3 Completion | 2020-04-20 | 1d | 2020-04-20 | All | Milestone
Complete | Non Critical Buffer | 2020-04-20 | 4d | 2020-04-24 | All | Non Critical Task
| Project Completion | 2020-04-24 | 1d | 2020-04-24 | All | Milestone
|  | Start | Duration
|  | 43905 | 1
|  | 43906 | 1
|  | 43906 | 1
|  | 43907 | 6
|  | 43907 | 6
|  | 43907 | 6
|  | 43907 | 6
|  | 43907 | 6
|  | 43907 | 6
|  | 43907 | 6
|  | 43907 | 6
|  | 43913 | 7
|  | 43913 | 7
|  | 43913 | 7
|  | 43913 | 8
|  | 43913 | 8
|  | 43913 | 8
|  | 43913 | 8
|  | 43913 | 8
|  | 43922 | 1
|  | 43923 | 7
|  | 43923 | 7
|  | 43923 | 7
|  | 43923 | 7
|  | 43923 | 7
|  | 43923 | 7
|  | 43930 | 6
|  | 43930 | 6
|  | 43930 | 6
|  | 43930 | 6
|  | 43930 | 6
|  | 43930 | 6
|  | 43936 | 1
|  | 43936 | 5
|  | 43936 | 5
|  | 43936 | 5
|  | 43941 | 5
|  | 43941 | 5
|  | 43941 | 5
|  | 43941 | 1
|  | 43941 | 4
|  | 43945 | 1